PART V: Risk Analysis and Project Estimation

V.1 Introduction

This section of the document outlines the updates for the risk analysis and the project estimates for the future. The purpose for this is to allow the developers to understand the underlying risks and estimates that might occur during Phase C of the software development.

V.2 Updates of Risk Analysis

V.2.1	Personnel shortfall

- Risk: Loss of a team member.

Risk Prevention: Find out about the background of every member. Look for past history of dropping courses. Use frequent communication to ensure everyone is doing work. Shift load between team members to make sure no one gets overwhelmed and drops the course.

- Risk: Team member not doing work.

Risk Prevention: Look at past history of each member, look for any past problems of working in groups. Share workload. Have members read to take over another member’s work if it becomes necessary. Make sure everyone is up to date and able to do different parts of the project. Use frequent communication and set internal deadlines to monitor everyone’s progress.

- Risk: Team member doing poor quality work.

Risk Prevention: Have more then one person responsible for any part of the project. Each member can check another member’s work to ensure quality. Weak programmers should be assigned less important tasks and should be helped.

V.2.2	Functional Requirements

- Risk: A function requirement is not implemented.

Risk Prevention: Make sure the work is fully split up and that everyone knows exactly what is going. Ensure that all requirements are implemented by performing extensive testing.

- Risk: A functional requirement implemented incorrectly.

Risk Prevention: Testing the functional requirements extensively is absolutely essential. Functional requirements should be double checked and given priority over everything else. Fixing these errors is a priority since any further delay could result in huge time/resource loss.

V.2.3	Bad external tasks

- Risk: Development environment customized at developer’s house may not be compliant with target (school) environments.

Risk Prevention: Deploy alpha versions in target environment frequently and check for compliance. Do not wait for the final product to deploy on the target environment for the first time. Read about potential compliance issues in the target environment.

V.2.4	Organization Issues

- Risk: Time allocated to tasks insufficient.

Risk Prevention: Consider change of management if it occurs frequently. Leave extra time when allocating time as buffer for possible unforeseen problems. Develop better estimation strategies to get more precise estimates.

V.3 Project Estimation

Project Estimation is used to allocate resources and budgets for this phase as well as to plan the schedule for the next phase. Project estimation includes estimation techniques as well as heuristics to determine the size and scope of the project.

V.3.1	Intra Project Estimation

This estimation is taken during the phase B of the project to provide the developers with a brief idea on how the amount of resources that have been consumed by the development team. This estimation is divided into comparing the original estimates with the current progress on the project and an update of estimates based on changes since the last documentation.

V.3.1.1	Tracking Original Estimates

From the documentation written during phase A, the only resource that we were able to compare was time since the project estimation done in the previous document only estimated time allocation.

The time required for deployment of the server exceeded the estimates by far. The Phase B deployment was planned to take at most a week but had instead taken over two weeks. The time resources spent on the deployment delayed other tasks.

V.3.1.2 	Response to Changes and Requirements

Any changes to the requirements at this point will require considerable amounts of resources. The functional requirements had already been dealt with in Phase A and if any changes do occur most of Phase A will have to be redone. Any new functional requirements would have to be implemented, incorporated and tested, a process which is very time consuming. Minor changes can at this time be done in reasonable time because the system is insufficiently complex to create serious problems.

Changes so far implemented to requirements such as the introduction of QuickUpload functionality, have forced the team to review system architecture and requirements and have been a serious time consumer.

V.3.2	Estimation Techniques

V.3.2.1	Intuition and Experience

Based on errors on previous estimates, the new time estimates will have to be increased by thirty percent per task. The new estimates will be based on expected length of time required for a task with the thirty percent leeway addition. This time buffer assigned to each tax will enable the team to deal effectively with any unexpected delays.

V.3.2.2	Problem Decomposing

Another way of getting better estimates requires that the work be further broken down into smaller pieces. While decomposing the work into smaller pieces the group gains a better understanding of what has to be done. For example, the deployment exceeded time expectations by hundred percent. This was caused by poor understanding of the complexity of the problem. If the problem had been broken down into smaller pieces and analyzed in greater detail, more effective approach could have been taken and a much better time estimate could have been derived.)